## SME Questions
PLB Universal Robotic Labeler REV-D — SME Question Register
TC 2412 Product Configurator — 150% BOM Construction ¦ Questions requiring SME confirmation before BOM can be finalised
# | Category | Priority | Question | If YES → | If NO → | Part IDs Involved | SME Answer | Notes / Action
INFEED
1 | Infeed | HIGH | ASSY_KIT_INFEED (A00021088) appears in BOTH the 6FT RH EU and 32FT LH NA BOMs at L2 inside the TLA. Does a PLB configuration exist where the machine ships WITHOUT an infeed module (Infeed = No)? | ASSY_KIT_INFEED carries: Infeed = Yes variant condition in TC | ASSY_KIT_INFEED becomes COMMON — no variant condition needed | A00021088 ASSY_KIT_INFEED A00008364 100_ASSY_INFEED A00021094 ASSY_INFEED_PACKAGING A00008445 140_ASSY_INFEED_BASE A00008400 WELDMENT_FRAME_INFEED |  | Blocks 5 PENDING_SME parts in 150% BOM
2 | Infeed | HIGH | ASSY_KIT_CONVEYOR_INFEED_EXTENSION (A00031581) sits at L1 in the 32FT LH NA BOM only. It is NOT in the 6FT EU BOM. Is this extension driven by Length = 32Ft alone — or only when BOTH Infeed = Yes AND Length = 32Ft are true? | Formula stays: Length = 32Ft AND Infeed = Yes (current assignment) | Formula changes to: Length = 32Ft only | A00031581 ASSY_KIT_CONVEYOR_INFEED_EXTENSION A00029953 ASSY_CONVEYOR_INFEED_EXTENSION A00032894 ASSY_CONVEYOR_INFEED_EXTENSION_PACKAGING A00032762 BLOCK_ALIGNMENT_INFEED |  | Determines Rule 13 formula in Inclusion Rules
LABEL APPLICATOR / ORIENTATION
3 | Label Applicator / Orientation | HIGH | Inside ASSY_KIT_LABEL_APPLICATOR, both MECHANISM_PRINT_RH and MECHANISM_PRINT_LH appear in BOTH BOMs (6FT EU and 32FT LH). Does the Label Applicator always ship with BOTH RH and LH print mechanisms in every configuration — regardless of machine orientation? | Both mechanisms are COMMON — no variant condition needed for all 19 Orientation-named parts inside Label Applicator | Each mechanism carries its own condition: MECHANISM_PRINT_RH → Orientation = RH MECHANISM_PRINT_LH → Orientation = LH | A00022307 MECHANISM_PRINT_RH A00022309 MECHANISM_PRINT_LH A00022312 POSITION_RULER_AND_TOGGLE_RH A00022313 POSITION_RULER_AND_TOGGLE_LH A00022322 SENSOR_MEDIA_RH A00022323 SENSOR_MEDIA_LH + 13 more RH/LH parts |  | Blocks 19 PENDING_SME parts — all inside Label Applicator kit
OUTFEED
4 | Outfeed | MEDIUM | ASSY_SENSOR_OUTFEED (A00016758) and WELDMENT_FRAME_OUTFEED (A00025728) appear in BOTH BOMs at L3 and L4 respectively. Are these parts shared across ALL outfeed types — or are they specific to Outfeed Type = Intralox only? | Both parts are COMMON — no variant condition | Both parts carry: Outfeed Type = Intralox | A00016758 ASSY_SENSOR_OUTFEED (L3) A00025728 WELDMENT_FRAME_OUTFEED (L4) |  | Determines if 2 parts are COMMON or carry Outfeed Type condition
5 | Outfeed | MEDIUM | The 32FT LH NA BOM Outfeed Panel is ASSY_OUTFEED_PANEL (A00034157) — this part has NO outfeed type suffix in its name. Is this panel specific to Outfeed Type = Intralox — or is it the standard panel used across ALL outfeed types including SWM? | Panel carries: Outfeed Type = Intralox | Panel is COMMON across all outfeed types | A00034157 ASSY_OUTFEED_PANEL (LH version) A00036378 ASSY_OUTFEED_PANEL (EU Intralox version) |  | Needed to finalise Inclusion Rule 15 and 16
LENGTH
6 | Length | MEDIUM | We found a reference to ASSY_ELECTRICAL_BOM_FOR_A00028494_PWR_PNL_5FT (A00032878) inside the 32FT LH BOM — suggesting a 5Ft electrical panel exists. Does a 5Ft PLB configuration exist in production? If yes, can you provide the BOM? | Add 5Ft to Feature Dictionary as confirmed value and provide 5Ft BOM for upload | 5Ft reference is historical — remove from Feature Dictionary pending values | A00032878 ASSY_ELECTRICAL_BOM_FOR_A00028494_PWR_PNL_5FT |  | BOM needed to confirm Length = 5Ft feature value
OUTFEED TYPE
CABLING / ARCHITECTURE
7 | Cabling / Architecture | LOW | The 32FT LH NA BOM has 25 explicit inter-module cable assemblies at L2 inside the TLA (e.g. ASSY_CABLE_INTERFACE_UPSTREAM_CTR1, ASSY_CABLE_WEIGHING_CONVEYOR_MOTOR_PWR2) that do NOT appear anywhere in the 6FT EU BOM. Does the 6FT EU machine have inter-module cable harnesses? If yes — where are they in the BOM? | Locate EU cable harnesses in BOM and verify they are correctly tagged COMMON or EU_RH | Confirm the 6FT EU machine uses a different cabling architecture — 25 cable assemblies are Length = 32Ft specific | A00021809 ASSY_CABLE_INTERFACE_UPSTREAM_CTR1 A00025086 ASSY_CABLE_WEIGHING_CONVEYOR_MOTOR_PWR2 A00025176 ASSY_CABLE_PRODUCT_CONVEYOR_PWR8 + 22 more ASSY_CABLE assemblies |  | Informational — does not block BOM finalisation
8 | Cabling / Architecture | MEDIUM | KIT_CABLE_DRAWINGS sub-assembly is present in all NA PLB assemblies, but is missing in EU PLB assembly. Is it a rule that Cable drawings will be available only in NA region | Add Formula Region=EU for KIT_CABLE_DRAWINGS |  | A00028083 KIT_CABLE_DRAWINGS_UNIVERSAL_ROBOTIC_LABELER_REV-D |  | Informational — does not block BOM finalisation
10FT LH NA — NEW QUESTIONS FROM 3-BOM ANALYSIS
9 | Infeed Extension (Formula Correction) | HIGH | The 10FT BOM contains ASSY_KIT_CONVEYOR_INFEED_EXTENSION (A00031581) — same part as in the 32FT BOM. This proves the original formula 'Length = 32Ft AND Infeed = Yes' was WRONG. CONFIRM: Is ASSY_KIT_CONVEYOR_INFEED_EXTENSION present in ALL configurations where Infeed = Yes — regardless of machine length? | Formula confirmed: Infeed = Yes (already updated in 150% BOM) | Provide the correct condition that drives this assembly | A00031581 ASSY_KIT_CONVEYOR_INFEED_EXTENSION A00029953 ASSY_CONVEYOR_INFEED_EXTENSION A00032894 ASSY_CONVEYOR_INFEED_EXTENSION_PACKAGING A00032762 BLOCK_ALIGNMENT_INFEED |  | Formula already updated in 150% BOM based on 3-BOM evidence — needs SME sign-off
10 | Outfeed Sensor (Different Part ID) | HIGH | The 10FT BOM uses a DIFFERENT Part ID for the outfeed sensor: 6FT EU: A00016758 ASSY_SENSOR_OUTFEED 32FT LH: A00016758 ASSY_SENSOR_OUTFEED (same) 10FT LH: A00027265 ASSY_SENSOR_OUTFEED (DIFFERENT) Why does the 10FT machine use a different sensor? Is this driven by Length = 10Ft — or a different revision? | Length driven: A00016758 → 6FT + 32FT A00027265 → 10FT only Formula: Length = 10Ft | Revision only — A00027265 is a direct replacement for A00016758 | A00016758 ASSY_SENSOR_OUTFEED (6FT EU + 32FT LH) A00027265 ASSY_SENSOR_OUTFEED (10FT LH only) |  | New finding from 3-BOM merge — determines formula for A00027265
11 | Outfeed Panel (3 Different Part IDs) | HIGH | All 3 BOMs use DIFFERENT Part IDs for ASSY_OUTFEED_PANEL: 6FT EU: A00036378 ASSY_OUTFEED_PANEL 32FT LH: A00034157 ASSY_OUTFEED_PANEL 10FT LH: A00025617 ASSY_OUTFEED_PANEL What drives these 3 different panels? (a) Outfeed Type (Intralox vs SWM) (b) Length (6Ft vs 10Ft vs 32Ft) (c) Both Length AND Outfeed Type | (a) Outfeed Type driven: A00036378 → Outfeed Type = Intralox Others need further SME input | (b) Length driven: A00036378 → Length = 6Ft A00034157 → Length = 32Ft A00025617 → Length = 10Ft | A00036378 ASSY_OUTFEED_PANEL (6FT EU) A00034157 ASSY_OUTFEED_PANEL (32FT LH) A00025617 ASSY_OUTFEED_PANEL (10FT LH) |  | Critical — determines variant formula for all 3 outfeed panels
12 | Outfeed Guide (10FT unique assembly) | MEDIUM | The 10FT BOM has a unique guide assembly not present in 6FT or 32FT: A00033707 ASSY_GUIDE_10FT_LH (L3 — 10FT only) The 32FT BOM has ASSY_GUIDES_32FT_LH (A00032586). The 6FT EU BOM has no equivalent guide. Is ASSY_GUIDE_10FT_LH driven by Length = 10Ft AND Orientation = LH — or Length = 10Ft only? | Formula: Length = 10Ft AND Orientation = LH (matches 32FT equivalent) | Formula: Length = 10Ft only | A00033707 ASSY_GUIDE_10FT_LH A00032586 ASSY_GUIDES_32FT_LH (32FT equivalent) A00032600 SIDEGUIDE_OUTFEED (10FT unique) |  | Add to Inclusion Rules — formula to be confirmed
13 | Cable Drawings Formula (Shared with 10FT) | MEDIUM | KIT_CABLE_DRAWINGS (A00028083) appears in BOTH 32FT LH and 10FT LH BOMs with the SAME Part ID. The current formula 'Length = 32Ft AND Region = NA' is WRONG — it is not Length = 32Ft specific. Is KIT_CABLE_DRAWINGS driven by Region = NA AND Orientation = LH — shared across all NA LH lengths? | Formula updated to: Region = NA AND Orientation = LH (not Length specific) | Separate cable drawing kits per length — provide correct Part IDs per length | A00028083 KIT_CABLE_DRAWINGS_UNIVERSAL_ROBOTIC_LABELER_REV-D (Present in both 32FT LH and 10FT LH — same Part ID) |  | Update Inclusion Rule 15 formula if YES
14 | Infeed Extension Sub-assembly Depth | MEDIUM | The 32FT BOM has additional infeed extension frame parts that do NOT appear in the 10FT infeed extension: 32FT only: ASSY_FRAME_CONVEYOR (A00030044), PLATE_BED (A00029701), PLATE_BED (A00029756) Does the 10FT infeed extension use a shorter/simpler conveyor than the 32FT version? | Yes — 10FT infeed extension is shorter. Sub-assemblies within the extension carry additional Length conditions | No — the parts are the same. Missing parts are BOM authoring difference only | A00030044 ASSY_FRAME_CONVEYOR (32FT only) A00029701 PLATE_BED (32FT only) A00029756 PLATE_BED (32FT only) |  | Determines if sub-conditions exist within infeed extension hierarchy
15 | Length = 10Ft Feature Confirmation | LOW | The Feature Dictionary previously listed 10Ft as PENDING with no BOM evidence. The 10FT BOM (A00027124) uploaded in this session confirms Length = 10Ft as a valid feature value. CONFIRM: Is A00027124 PLB_UNIVERSAL_ROBOTIC_LABELER_REV-D_10FT_LH_NA the correct and current production BOM for the 10FT LH NA configuration? | Length = 10Ft confirmed Feature Dictionary updated — 10Ft moved from pending to confirmed | BOM provided is incorrect — provide the correct 10FT BOM file | A00027124 PLB_UNIVERSAL_ROBOTIC_LABELER_REV-D_10FT_LH_NA (Root Part ID of uploaded BOM) |  | Feature Dictionary already updated — formal sign-off required
SUMMARY — Questions Required Before 150% BOM Finalisation
Questions | Category | Priority | Impact
Q1 + Q2 | Infeed | HIGH | Must be answered — 5 PENDING_SME parts + Rule 13 formula blocked
Q3 | Label Applicator | HIGH | Must be answered — 19 PENDING_SME parts blocked
Q4 + Q5 | Outfeed | MEDIUM | Needed to finalise Inclusion Rules 15 and 16
Q6 + Q7 | Length | MEDIUM | BOMs needed to confirm 5Ft, 10Ft, 15Ft feature values
Q8 | Outfeed Type | MEDIUM | BOM needed to confirm SWM feature value
Q9 | Cabling | LOW | Informational — does not block BOM finalisation
Q9–Q15 | 10FT LH NA | 🔴/🟡 HIGH/MEDIUM | 7 new questions from 3-BOM analysis — Q9+Q10+Q11 are HIGH priority (formula corrections). Q12+Q13+Q14 MEDIUM. Q15 LOW (confirmation only).